## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Phoenixes
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a user I want to get a single product so that I can view the information of that product | Given I click on a product when the product exists then I should be directed to that products page and shown it's information | Pass | MR 22/10 | Pass | MR 20/11
As a user I want to see a list of all products on the website so that I can browse them and decide what I want to buy | GIVEN I click on the products list WHEN I'm not on the products list page THEN I should be redirected to the products list page | Pass | AA 22/10 | Pass | AA 20/11
| GIVEN I click on the products list WHEN I'm the products list page THEN I should stay on the page | Pass | AA 22/10 | Pass | AA 20/11
As a user I want to search for products so that I can find products related to what I want more easily | GIVEN that I input an search term to be searched WHEN items with the search term in their name exist THEN the website should display the list of those products | Pass | HK 22/10 | Pass | HK 20/11
| GIVEN that I input an search term to be searched WHEN no items with the search term in their name exist THEN the website should show a message indicating that there are no search results | Pass | HK 22/10 | Pass | HK 20/11
As an owner I want to create a new product so that it becomes available for purchase on the website | GIVEN I enter attributes of a product WHEN no product with the given name exists THEN the system should create the product, add it to the inventory, save to the persistent store, and now show it on the user interface products list | Pass | KA 22/10 | Pass | KA 20/11
| GIVEN I enter attributes of a product WHEN a product with the given name already exists THEN the system should display a message indicating an error | Pass | KA 22/10 | Pass | KA 20/11
As an owner I want to submit a request to delete a single product so that it is no longer in the inventory. | GIVEN I click a a button WHEN the product exists THEN the system should delete the product from the inventory, update the persistence file and display a message indicating it was successfully deleted | Pass | KA 22/10 | Pass | KA 20/11
As an owner I WANT to submit a request to update a product in the inventory SO THAT I can change a property of the product | GIVEN I enter new properties for a product WHEN the properties are valid THEN the product should be updated in the inventory and the system should display a message indicating it was successfully updated | Pass | ME 22/10 | Pass | ME 20/11
| GIVEN I enter new properties for a product WHEN the properties are invalid THEN the product should not be updated and the system should display a message indicating that the product was not updated successfully | Pass | ME 22/10 | Pass | ME 20/11
As a buyer I want to add products to my shopping cart so that I register what I want to purchase. | Given that I press "add to cart" when the product is not in my cart and I'm logged in then the product should appear in my cart |  |  | Pass | HK 20/11
As a buyer I want to remove products from my shopping cart so that I remove what I don't want to purchase. | Given that I press "remove from cart" when the product is in my cart then the product should be removed from the cart |  |  | Pass | AA 20/11
As a buyer I want to purchase products in my shopping cart so that I receive them. | Given that I press "Checkout" when there are products in my cart then I should proceed to the payment system |  |  | Pass | ME 20/11
| Given that I try press "Checkout" when there are no products in my cart then I receive a message indicating that there's no items in my cart |  |  | Pass | ME 20/11
As a buyer I want to order products in my shopping cart as gifts so that I send them to another person with nice decorations. | Given that I try tick "Order is a gift" when entering the order details then the order should be considered a gift order |  |  | Pass | ME 20/11
As a user I want to choose a wood type on the product so that it's something I like. | Given I choose a wood type when it's in stock then the product can be added to cart |  |  | Pass | KA 20/11
As a user I want to logout so that I'm no longer logged in | Given I press logout when I'm logged in then I expect to be logged out |  |  | Pass | MR 20/11
Given I submit my username when my username is not in the system then I expect to be prompted to create an account | Given I submit my username when my username is in the system then I expect to be logged in and moved to the homepage |  |  | Pass | KA 20/11
| Given I submit my username when my username is not in the system then I expect to be prompted to create an account |  |  | Pass | KA 20/11